## Current Iteration
|  | Iteration Number: |  |  |  | 4
|  | Expected Total effort: |  |  |  | 35
|  | Days In Sprint: |  |  |  | 5
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Basic frontend | 8 | Days (Points Completed) 1: 8 | 0 | 100%
"Trending posts" algoritme | 6 | [20 empty] | 6 | 0%
Opret bruger | 3 | Days (Points Completed) 1: 3 | 0 | 100%
Bruger login | 3 | Days (Points Completed) 1: 3 | 0 | 100%
Opret en kommentar | 3 | [20 empty] | 3 | 0%
Rediger sin egen kommentar | 2 | [20 empty] | 2 | 0%
Slet sin egen kommentar | 2 | [20 empty] | 2 | 0%
Up/donwvote opslag | 1 | [20 empty] | 1 | 0%
Up/downvote kommentar | 1 | [20 empty] | 1 | 0%
Opslags-historik | 2 | [20 empty] | 2 | 0%
Kommentar-historik | 2 | [20 empty] | 2 | 0%
GIF upload | 1 | [20 empty] | 1 | 0%
Video upload | 1 | [20 empty] | 1 | 0%
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 35 | 21 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21 | 40%
Ideal Trend | 35 | 28 | 21 | 14 | 7 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days